|  | Oman LNG LLC Qalhat |
| --- | --- |

# contract title

#### Section B2

SPECIAL CONDITIONS OF CONTRACT

# Tender Number xx-xx-xxxx

# Clause 1 – DEFINITIONS

  - Article 1 is hereby amended to include the following definition:

- “CALL-OFF VALUE” means the total monetary amount authorized by COMPANY for a specific call-off or purchase order under this CONTRACT. Such amount shall be separately identified in the relevant call-off documentation and is the maximum sum CONTRACTOR is entitled to invoice for that particular scope of services or WORK, unless otherwise agreed in writing by the COMPANY.

# Clause 40 – DELAYS TO COMPLETION

  - Sub-Clause 40.1 is hereby deleted and replaced by the following:

40.1       Delay in Completion of Fixed Lump Sum WORK

If CONTRACTOR fails to complete the WORK under a lump sum CALL-OFF, Schedule 1 of Section E (or any part thereof) within the period specified, or within any extension granted in writing by the CONTRACT HOLDER, CONTRACTOR shall pay COMPANY liquidated damages at a rate of zero-point five percent (0.5%) of the CALL-OFF VALUE for each day of delay beyond the agreed completion date of that CALL-OFF, up to a maximum of ten percent (10%) of the CALL-OFF VALUE.

If only a portion or sub-task of the WORK under a CALL-OFF is delayed, liquidated damages shall be calculated based on the portion of the CALL-OFF VALUE attributable to the delayed work, as reasonably determined by the breakdown or schedule of rates.

  - Sub-Clause 40.2 is hereby deleted and replaced by the following:

40.2       Delay in Completion of Unit Priced WORK

If CONTRACTOR fails to complete the WORK covered by Schedules 2, 3, and 4 and TPM/TPS of Section E (or any part thereof) within the period specified, or within any extension granted in writing by the CONTRACT HOLDER, CONTRACTOR shall pay COMPANY liquidated damages at a rate of one percent (1%) of the CALL-OFF VALUE for each day of delay beyond the agreed completion date of that CALL-OFF, up to a maximum of ten percent (10%) of the CALL-OFF VALUE.

If only a portion or sub-task of the WORK under a CALL-OFF is delayed, liquidated damages shall be calculated based on the portion of the CALL-OFF VALUE attributable to the delayed work, as reasonably determined by the breakdown or schedule of rates.

  - Sub-Clause 40.3 is hereby deleted and replaced by the following:

40.3       Delay in Mobilization:

If CONTRACTOR fails to commence the WORK in accordance within the mobilization duration stipulated in Clause 3 of Section D, and such failure is neither attributable to force majeure (as defined in Section B1) nor due to a default by COMPANY GROUP, CONTRACTOR shall pay COMPANY liquidated damages at a rate of one percent (1%) of the CALL-OFF VALUE for each day of delay beyond the mobilization duration stipulated in Section D, up to a maximum of ten percent (10%) of the CALL-OFF VALUE unless otherwise specified in SECTION E Schedule of Prices.

  - Sub-Clause 40.4 is hereby amended as the following:

40.4     In no event shall the sum of CONTRACTOR's liability to COMPANY under any CALL-OFF for all delay liquidated damages assessed further to this Clause 40 exceed, in the aggregate, fifteen percent (15%) of the CALL-OFF VALUE unless otherwise specified in SECTION E Schedule of Prices.  In the event that CONTRACTOR's liability for delay liquidated damages under any CALL-OFF exceeds this fifteen percent (15%) threshold, the COMPANY shall have the right, at its absolute discretion, to terminate the CONTRACT.

(AI to identify and draft clauses where deviate from B 1 clauses)